NWDPWR – THE PAYMENT SYSTEM Project Charter

CONTRACT NO: PWR 107/22

DESCRIPTION: TO PROJECT, PROGRAMME AND PORTFOLIO MANAGEMENT (PPPM) SERVICES FOR THE NORTHWEST DEPARTMENT OF PUBLIC WORKS AND ROADS FOR A PERIOD OF THIRTY-SIX (36) MONTHS

DOCUMENT CONTROL SHEET

The purpose of this form is to ensure that documents are reviewed and approved prior to issue. The form is to be bound into the front of all documents issued by GO BENG DBG PROJECTS (PTY) LTD JOINT VENTURE.

DOCUMENT PROPERTIES

| Item | Description |
| --- | --- |
| Document Title | NWDPWR – THE PAYMENT SYSTEM Project Charter |
| Client | NORTH WEST PUBLIC WORKS AND ROADS |
| Consultant | GO BENG CONSULTING - DBG PROJECTS (PTY) LTD JOINT VENTURE |
| Document Status |  |
| Date |  |

VERSION CONTROL

| Version | Prepared By | Signature |
| --- | --- | --- |
| FIRST DRAFT | Nelisiwe Mnyazana |  |
| Version | Reviewed By | Signature |
| FIRST REVIEW | Stefan van Tonder |  |
| Version | Approved By | Signature |
| SECOND REVIEW |  |  |

APPROVED FOR EXTERNAL ISSUE BY

| Version | Approved By | Signature |
| --- | --- | --- |
| FINAL REPORT | Phumza Smith |  |

TABLE OF CONTENTS

1.	Executive Summary	5

2.	Project Business Benefits	7

3.	Project Assumptions	8

4.	Project high-level scope	9

4.1.1	System Implementation and Deployment	10

4.2.1	Hosting Infrastructure	11

4.2.2	External System Transactional Integration (Initial Phase)	11

4.2.3	Legacy System Decommissioning	12

4.2.4	Policy and Regulatory Reform	12

4.2.5	Maintenance of Third-Party Systems	12

4.2.6	Long-Term System Enhancements	13

4.2.7	Broader Organisational Change Programmes	13

5.	Key milestones	13

6.	Governance, Communication and Oversight	15

7.	Roles and Accountability	22

8.	Project Risk	30

9.	Change and Configuration Management	33

10.	Change Management and User Adoption	35

11.	Technology and Infrastructure Readiness	36

12.	Deliverables	38

ABBREVIATIONS

AG - Auditor-General

AOPO - Audit of Predetermined Objectives

AOP – Annual Operational Plan

APP - Annual Performance Plan

CREAM – Clear, Relevant, Economic, Adequate and Monitorable Principle

DPME - National Department of Monitoring and Evaluation

EPWP - Expanded Public Works Programme

FMPPI - Framework for Managing Programme Performance Information

KPI - Key Performance Indicator

MEC - Member of Executive Council

MTDP - Medium Term Development Plan

MTEF - Medium Term Expenditure Framework

NDP - National Development Plan

NMTDP - National Medium-Term Development Plan

NDPW - National Department of Public Works

NWDPWR – North West Department of Public Works and Roads

SMART - Specific, Measurable, Achievable, Relevant, and Time-bound Principle

SOPA - State of Province Address

SP – Strategic Plan

PFMA - Public Finance Management Act

POE - Portfolio of Audience

PPPMU - Project, Programme and Portfolio Management Unit

TID – Technical Indicator Description

# Executive Summary

The North West Department of Public Works and Roads (NWDPWR) are responsible for implementing several vital initiatives aimed at fostering community development and alleviating poverty. Central to these efforts is the Community-Based Programme (CBP), a key component of the broader Expanded Public Works Programme (EPWP). The CBP focuses on creating employment opportunities, developing assets, enhancing skills, and improving infrastructure within local communities.

To support these objectives, an effective payment system is essential. This system is designed to manage various financial and administrative functions, including the disbursement of stipends, UIF, COIDA payments, medical assessments, participant supervision, training programs, and the procurement of Personal Protective Equipment (PPE) and tools for participants engaged in Programme 4: Community-Based Programme (CBP).

## Project Objectives

The main objective of the CPIMS project is to assist and support the Department in the following areas:

- To establish a Payment System, where the system is planned to cater for the functions of programmes of the department namely:

- Programme 4: Community-Based Programmes – Enabling effective management and reporting of the Contractor Development Programme (CDP) and Expanded Public Works Programme (EPWP).

- Strategic Objective

- Establish a single source of truth for delivery.

- Improve planning, budgeting, and expenditure control.

- Operational Objective

- Migrate verified and cleansed legacy data into the system.

- Implement user-based security and role-driven workflows.

- Ensure SITA-aligned hosting, cybersecurity, and network readiness.

- Governance Objective

- Implement a formal governance structure with approved Terms of refrences (TORs).

- Institutionalise a CRAIDs register.

- Implement an integrated risk management process.

- Formalise stakeholder and communication management.

- Establish change and configuration management control.

# Project Business Benefits

Business Benefits of Implementing the Payment System:

- Enhanced Stakeholder Engagement and Buy-in: Establishing dedicated workflows ensures active involvement and commitment from Programme Managers, fostering a collaborative environment that accelerates system adoption.

- Customized Solutions for Greater Relevance: Allowing workstream to define their specific system requirements ensures the system is tailored to meet the unique needs of the programme, improving efficiency and user satisfaction.

- Streamlined Data Migration and Centralized Information: Coordinated efforts by the programme to compile, collate, and migrate data onto the system will result in a single, reliable source of project information, reducing duplication and minimizing errors.

- Improved Monitoring and Reporting: Assigning responsibility to programme leads for tracking and reporting progress on system rollout provides real-time insights, enabling proactive decision-making and faster issue resolution.

- Effective Change Management and System Adoption: Having programme managers champion the system ensures that the rollout is well-received, fostering a culture of acceptance and maximizing the value derived from the payment system.

- Overall Business Efficiency: By integrating project data, standardizing processes, and enhancing reporting capabilities, the system will lead to better project oversight, cost control, and timely delivery of infrastructure projects.

# Project Assumptions

The Payment System Project will be delivered based on the following key assumptions. These assumptions underpin the agreed scope, timelines, and delivery approach.

- Governance structures, including the Steering Committee, will meet as scheduled to review progress, resolve escalated issues, and approve key decisions

- Business stakeholders will be available to participate in requirements validation, design reviews, testing, training, and acceptance activities on a per-module basis.

- Business users will provide timely input, feedback, and sign-off

- Programme managers will be available during critical delivery periods, including testing and go-live activities.

- Scope changes outside of what is defined in the approved Project Scope will be managed through formal change control.

- Data provided for migration and testing will be of sufficient quality and completeness to support planned activities.

- Project documentation, configuration artefacts, and decision records will be maintained in PPMU approved repositories.

- Knowledge transfer and documentation will be sufficient to support continuity of delivery and transition to operational support.

# Project high-level scope

  - In Scope

### System Implementation and Deployment

The project includes the design, configuration, development, and deployment of the Payment Systems the Department’s enterprise platform for infrastructure and asset lifecycle management.

** A detailed defined scope will be documented in the Payment SystemScope document.

This includes the core functional components of the Payment System module

- CBP Community Based Programme Management Module (Contractor Development Programme, EPWP)

Data Migration and Validation

- Extraction of existing asset data from manual spreadsheets and legacy systems.

- Data cleansing, validation, and migration into the new centralized system.

- Ensuring data accuracy, integrity, and security during migration.

System Integration

- Establishing real-time data exchange and process automation across integrated platforms.

Operationalization & Training

- Establishment of workflows and user roles within the system.

- Training of departmental staff for effective use and management of the platform.

Post-Implementation Support

- Providing ongoing support, maintenance, and updates for 36 months post-launch.

- Addressing system issues, user support, and performance optimization during this period.

Reporting & Documentation

- Development of reporting dashboards and analytics capabilities.

- Comprehensive documentation covering system architecture, user manuals, and maintenance procedures.

Payroll

- Stipend disbursement processing, execute monthly stipend payments based on attendance and work records, adhering to scheduled disbursement dates.

- Generation of payslips, automatically generate individual payslips for participants, ensuring transparency and record accuracy.

- Statutory deductions management, calculate and deduct statutory contributions such as PAYE, SDL, UIF, and COIDA, ensuring compliance with legal requirements.

- Reporting and reconciliation, provide detailed payroll reports, including payment summaries, reconciliation of payments against attendance records, and compliance reports for audit purposes

  - Out of Scope

### Hosting Infrastructure

The procurement and supply of:

- Hosting platforms

- Servers

- Storage

- Network infrastructure

- End-user devices remain the responsibility of the Department and are excluded from this project scope.

### External System Transactional Integration (Initial Phase)

Live integration with:

- BAS

- SmartGov

- RAMS

- DeedsWeb

or any other external system is excluded from the initial implementation phase and will be treated as separate workstreams and will be formally scoped and costed and will follow the approved change control process.

### Legacy System Decommissioning

The decommissioning of any legacy system other than the approved data sources for the payment systemmigration is excluded.

### Policy and Regulatory Reform

The project does not include:

- Development of new legislation

- Amendment of departmental policies

- Institutional restructuring

beyond alignment of business processes to the system.

### Maintenance of Third-Party Systems

The project excludes:

- Maintenance

- Upgrades

- Support

for BAS, SmartGov, RAMS, DeedsWeb, or any other external system.

### Long-Term System Enhancements

Major enhancements and functional expansion beyond the defined implementation project will be managed as separate projects.

### Broader Organisational Change Programmes

Department-wide organisational transformation initiatives not directly linked to system adoption are excluded.

  - Scope Control

Any item not explicitly defined as in scope will be treated as out of scope and will follow the approved change control process through the Technical Steering Committee acting as the Change Control Board.

# Key milestones

Key milestones represent formal stage gates that confirm readiness to progress between phases, support governance oversight, and enable controlled delivery of the project.

Program level milestones apply once across the project.

  - High-level Milestone – Deliverable Mapping

| Milestone ID | Milestone | Primary Deliverables | Aligned Grouping | Indicative Timing |
| --- | --- | --- | --- | --- |
| M1 | Project initiation & Planning Complete | - Approved Scope - Approved Project Charter - Approved Project Plan - Approved Post Implementation Support - Approved System Architecture - Approved Change Management - Steering Committee and project meeting packs, minutes, and action logs initiated - Commencement of regular project status reporting | PMO – Project Governance | End of Project Mobilisation |
| M2 | Needs Analysis Baseline and Approval | - Functional requirements baseline | Requirements & Design | End of Requirements Definition |
| Programme level milestones – will be applied iteratively for each module for sequential roll-out |  |  |  |  |
| M3 | System Configuration & Build Complete | - Configured solution - Configured reports and dashboards | Configuration, Build & Integration | End of Programme Build |
| M4 | System Testing | - Data migration - Defect resolution to agreed quality thresholds - Confirmation of readiness for User Acceptance Testing | Enablement & Validation | End of Programme Testing |
| M5 | System UAT Sign-Off & Go-Live | - Completed User Acceptance Testing with formal sign-off - User training materials and execution of role-based training sessions - Approved user readiness for production deployment - Successful module deployment to production | Enablement & Validation / Go-Live & Operational Support | Programme Go-Live |
| M6 | Final System Go-Live & Stabilisation Entry | - Completion of final programme go-live - Handover documentation and knowledge transfer - Establishment of operational support arrangements - Commencement of post-implementation stabilisation (hypercare) | Go-Live & Operational Support | Final System Go-Live |
| M7 | Stabilisation Exit & Project Closure | - Completion of post-implementation stabilisation - Formal handover to steady-state support - Final project reporting and closure documentation - Formal project sign-off | Go-Live & Operational Support / PMO | End of Stabilisation Period |

# Governance, Communication and Oversight

  - Executive Authority

Programme Sponsor: Mr IM Kgantsi (HOD DPWRNW)

Programme Manager: Phumza Smith (PPPMU)

Project Manager: Nelisiwe Mnyazana (PPPMU)

| Organisation | Job Title | Responsibility |
| --- | --- | --- |
| DPWRNW | Project Sponsor | Overall executive accountability for the DPWRNW Project, including strategic oversight and approval of key decisions and deliverables. |
| PPPMU | Programme Manager | Provides executive oversight on behalf of the service provider, supports escalation resolution, ensures senior-level engagement, and provides delivery assurance in line with contractual obligations |
| DPWRNW/PPPMU | Steering Committee | Provides strategic oversight, resolves escalated risks and issues, and approves major project decisions. |
| DPWRNW/PPMU | Business Owner – SCM (across different SCM functions) Project Team | Accountable for business requirements, solution acceptance, and realisation of business benefits. |
| PPPMU | Project Manager | Responsible for day-to-day project management, governance, reporting, and coordination. Responsible for managing solution delivery activities and ensuring delivery in accordance with the department standards the approved scope and timelines. |

  - Steering Structures

Main Steering Committee

Provides strategic oversight, approves scope, budget, and policy decisions.

Technical Steering Committee

- Provides operational governance for:

- System design and configuration

- Risk and change control

- Integration and architecture

- Data and security compliance

Both structures operate in terms of formally approved Terms of Reference and defined meeting cycles.

- Delivery Stand-ups (Twice Weekly)

- Project Progress Report (Monthly)

- Steering Committee Meetings (Monthly)

- Ad hoc Communications (email, meetings)

  - Milestone Review & Approval Matrix

| Milestone ID | Milestone | Review or Approval Authority |
| --- | --- | --- |
| M1 | Project Mobilisation & Planning Complete | Project Sponsor and PPPMU |
| M2 | Needs Analysis Baseline Approved | Programme owner/ Project Sponsor/ PPMU |
| M3 | System Configuration & Build Complete | PPMU/ with Programme owner oversight |
| M4 | System Testing Complete | PPMU/ with Programme owner oversight |
| M5 | System e UAT Sign-Off & Go-Live | PPMU/ with Programme owner oversight |
| M6 | Final Programme Go-Live & Stabilisation Entry | Steering Committee |
| M7 | Stabilisation Exit & Project Closure | Project Sponsor |

  - BUDGET

  - Capital Expenditure

| Description | Cost to Deliver (Excl. VAT) |
| --- | --- |
| Analysis and Design, including Technical Specifications, Architecture Design |  |
| Build / Development / Configuration |  |
| Testing, including Functional, Performance, Penetration Testing and Vulnerability Scanning |  |
| Hosting Environment (Development, Test and Production environments) |  |
| Licences |  |
| Total Approved CAPEX Budget |  |

  - Operating Expenditure

| Description | Cost to Deliver (Excl. VAT) |
| --- | --- |
| Support and Maintenance – Year 1 |  |
| Support and Maintenance – Year 2 |  |
| Total Approved OPEX Budget |  |

  - Total Project Cost

| Description | Cost to Deliver |
| --- | --- |
| Total CAPEX + OPEX (Excluding VAT) |  |
| Total CAPEX + OPEX (Including VAT) |  |

# Roles and Accountability

The successful delivery of the Comprehensive Infrastructure Project Management System (THE PAYMENT SYSTEM) is dependent on clearly defined, formally assigned, and actively executed roles and responsibilities across the governance, business, and technical environments of the North West Department of Public Works and Roads.

This section establishes the accountability framework that will ensure:

- Effective decision-making

- Proper oversight and control

- Segregation of duties

- Traceability of approvals

- Alignment between business ownership and technical implementation

- Compliance with departmental governance and audit requirements

The roles defined in this Charter operate within the approved project governance structure and are mandatory for all project participants, including departmental officials, programme representatives, ICT, and PPPMU.

Each role carries:

- A clearly defined mandate

- Decision rights

- Approval authority

- Performance accountability.

Responsibilities are allocated in a manner that:

- Ensures business ownership of requirements, data, and user acceptance

- assigns technical accountability for solution design, configuration, and performance

- Maintains executive oversight for strategic direction, funding, and phase

- Provides independent assurance through risk, finance, SCM, and internal audit participation.

To support transparency and control, a formal RASCI model will be applied to all key deliverables and stage-gate approvals. This will ensure that:

- No deliverable is produced without an accountable owner

- No approval is granted without the appropriate authority

- All decisions are auditable and formally recorded.

this structured allocation of roles and responsibilities directly addresses the need for strengthened governance, improved control over project execution, and enhanced accountability for the achievement of project outcomes.

  - Project Roles

The Payment System` project is executed through a multi-tier governance and delivery structure that brings together executive leadership, programme management, structures units, ICT, and the implementation partner.

Each role defined in this Charter represents a specific level of authority and accountability within the project and is aligned to:

- Strategic oversight

- Operational delivery

- Technical governance

- Business ownership

- Assurance and compliance.

the roles are structured to ensure that:

- strategic decisions are taken at the appropriate executive level

- technical decisions are governed through the Technical Steering Committee

- operational execution is coordinated through the Project Manager

- programme and business units retain ownership of their processes, data, and user acceptance

- independent control functions provide oversight over financial, contractual, and risk-related matters.

All roles defined in this Charter are formally recognised project roles and are not advisory in nature.

Role holders are required to actively participate in governance structures and fulfil their decision-making and approval responsibilities.

**Please refer to the  stakeholder matrix document for stakeholder detail

| Stakeholder | Role | Interest | Engagement Strategy |
| --- | --- | --- | --- |
| Head of Department (HOD) | Executive Authority | High | Manage closely – Regular executive briefings |
| CIO | System Owner | High | Manage closely – Steering committee member |
| Programme Managers (Workstream 1-4) | operational Leads | High | Keep engaged – Workshops & progress meetings and training etc |
| End Users | System Users | High | Keep informed – Training & communications |
| PPMU Project Team | Implementation Partner | High | Active collaboration & governance meetings |
| Internal Audit | Compliance | Low | Periodic compliance updates |

  - Project Responsibilities

Project responsibilities are defined to ensure that every component of the Payment Systemimplementation is planned, executed, controlled, and approved in a structured and auditable manner.

Responsibilities are grouped across five control dimensions:

- Strategic Governance

- Project Delivery Management

- Business Ownership and User Adoption

- Technical Governance and Solution Control

- Assurance and Compliance

All responsibilities are formally assigned to specific roles and governance structures and are executed through:

- stage-gate approvals

- controlled deliverables

- documented decision-making

- performance reporting.

this approach ensures that the THE PAYMENT SYSTEM project operates within a controlled governance environment and that accountability for delivery is clearly defined and enforceable.

  - RASCI Responsibility Assignment Framework

To ensure clear accountability, effective governance, and auditable decision-making throughout the Comprehensive Infrastructure Project Management System (THE PAYMENT SYSTEM) implementation, the project will apply a formal RASCI responsibility assignment model to all key deliverables, processes, and stage-gate approvals.

The RASCI model provides a structured method for defining and documenting the level of involvement of each role in the execution and control of project activities. Its application ensures that responsibilities are unambiguous, duplication of effort is avoided, and decision-making authority is exercised at the appropriate level within the governance framework of the North West Department of Public Works and Roads.

  - RASCI Role Definitions

R – Responsible

The role that performs the work required to complete the activity or produce the deliverable. Responsibility may be shared where multiple parties contribute to execution; however, responsibility for delivery remains clearly defined and measurable.

A – Accountable

The role that has ultimate ownership of the outcome and the authority to approve the deliverable. Only one role is accountable for each activity to ensure clear decision-making and governance control.

S – Supports

Roles that provide resources, expertise, or operational assistance to enable successful completion of the activity. These roles do not carry approval authority but are essential to execution.

C – Consulted

Roles that must be formally engaged prior to a decision or deliverable being finalised. Consultation is a two-way process and ensures that inputs from subject matter experts, control functions, and affected stakeholders are incorporated.

I – Informed

Roles that must be kept informed of progress, decisions, or outcomes. This ensures transparency, alignment, and organisational awareness without creating approval bottlenecks.

  - RASCI Chart

| Activity | HOD | CIO | Project Manager | Programme Managers | Finance | PPMU Project Team |
| --- | --- | --- | --- | --- | --- | --- |
| Project Approval | A | C | R | I | C | I |
| Requirements Definition | I | C | A | R | C | C |
| System Design and implementation | I | A | R | C | I | R |
| Data Migration | I | C | A | R | I | R |
| Testing & Validation | I | C | A | R | I | R |
| Go-Live | A | C | R | C | I | C |
| 36-MonthsSupport | I | A | R | C | I | R |

# Project Risk

  - Purpose

Risk and CRAIDs management is implemented as a formal, continuous control process to ensure that all events or conditions that may impact the successful delivery of the Comprehensive Infrastructure Project Management System (THE PAYMENT SYSTEM) are:

- proactively identified

- consistently assessed

- formally recorded

- actively managed

- escalated through the appropriate governance structures.

Table 1: Key Risks and Dependencies

| Item | Description | Mitigating Actions | Impact |
| --- | --- | --- | --- |
| System Hosting and Data Management | Concerns about where the system would be hosted and how data would be stored, particularly regarding the security and ownership of data | It was confirmed that data ownership always belongs to the client, and hosting can be performed either on the vendor’s infrastructure or the client’s infrastructure, depending on the client's preference. The vendor uses Docker containers for system deployment, which includes built-in backup and redundancy features. | Low |
| Redundancy and Failover | THE PAYMENT SYSTEM Redundancy and Failover: | The vendor outlined their use of Docker containers to ensure better redundancy and quick failover handling. In case of server failure, the system is designed to switch to a backup server with minimal downtime. | Low |
| Cybersecurity and System Security | Cybersecurity concerns were raised, particularly in the context of cloud hosting. | The vendor explained various security measures, including IP-based access restrictions to servers and the automatic prevention of malicious file uploads. The server is protected by restricted IP access, and files uploaded by users are stored securely to avoid the execution of malicious code. Security measures are in place to prevent SQL injection and unauthorized access to sensitive data. | Low |
| System Testing and Real-World Usage | The importance of testing the system in real-world conditions, particularly for network performance, was highlighted. It was suggested that we engage with current users to gather feedback on the system's strengths and weaknesses. | A Network capacity. This test plan ensures a systematic approach to capturing and analysing network traffic using Wireshark. The results will help identify issues, optimise performance, and ensure security compliance. The assessment test plan was developed. | Medium |
| The Payemnt SystemHosting | Delay from GITO to Infrastructure for THE PAYMENT SYSTEM Hosting | Escalate to the HOD’s office | High |

# Change and Configuration Management

The Comprehensive Infrastructure Project Management System (THE PAYMENT SYSTEM) will be implemented within a formally controlled change and configuration management environment to ensure that all modifications to approved baselines are evaluated, authorised, recorded, and communicated in a structured and auditable manner.

This control is essential to protect the integrity of the approved project scope, schedule, cost, solution design, and deliverables, and to prevent unauthorised or uncontrolled changes that may compromise governance, compliance, or service delivery objectives of the North West Department of Public Works and Roads.

Change and configuration management will operate as an integrated process that:

- Links business requirements to approved solution outputs

- Enforces version and baseline control

- Ensures impact-based decision-making

- Provides full traceability from request to implementation.

All changes will be processed through formally defined approval structures aligned to the project governance model, with the Technical Steering Committee acting as the Change Control Authority for solution, configuration, and baseline-related decisions.

This approach ensures that the project remains predictable, controlled, and aligned to its approved objectives while enabling managed flexibility where change is required.

A formal Change Management Process will be implemented to ensure:

- Structured submission and evaluation of change requests

- Impact assessments (scope, cost, schedule, benefits, resources)

- Defined approval authority

- Audit trail of decisions

A Configuration Management Plan will govern:

- Version control

- Baselines

- Release management

- Deliverable integrity

# Change Management and User Adoption

Change Management and User Adoption ensures that the implementation of The Payment Systemis not limited to system deployment but results in sustainable business transformation across all affected programmes. The introduction of an integrated digital platform represents a significant shift in how infrastructure planning, delivery, monitoring, and reporting are performed, and therefore requires a structured organisational transition approach.

This component focuses on preparing leadership, business units, and end users for the new ways of working through structured impact assessments, readiness evaluations, role-based training, and ongoing user support. It ensures that business processes are aligned to system workflows, that users understand their responsibilities within the new environment, and that resistance to change is proactively managed.

The change management approach includes stakeholder impact analysis, communication of the change vision, development of training materials, execution of training sessions, and post-implementation user support. Adoption will be monitored through measurable indicators such as system utilisation, data quality, compliance with defined processes, and user competency levels.

By embedding change management into the project governance framework, the Department ensures that THE PAYMENT SYSTEM delivers its intended strategic value, improves operational performance, and achieves long-term sustainability.

A Change Management Committee, comprising of Programme Managers, will:

- Champion adoption

- Drive user readiness

- Manage resistance to change

- Oversee training and business transition

# Technology and Infrastructure Readiness

Technology and Infrastructure Readiness confirms that the technical environment required to deploy, operate, support, and scale the The Payment System is available, compliant, and fit for purpose prior to go-live. This section establishes the governance and assurance mechanisms used to verify that all foundational ICT components including hosting, network capacity, security, system software, user access, and integration enablement meet the defined solution architecture and departmental standards.

The readiness assessment ensures alignment between the application solution delivered by the service provider and the Department’s enterprise architecture, ICT policies, cybersecurity requirements, and operational support model. It further provides formal evidence that the environment has been evaluated for performance, availability, capacity, business continuity, and disaster recovery to support a stable production implementation.

This process includes verification of:

- Provisioning and configuration of the approved hosting environment (as supplied outside this project scope)

- Network connectivity and accessibility across head office, districts, and relevant operational sites

- Identity and access management, user provisioning, and role-based security

- Compliance with government ICT security and data protection standards

- Availability of non-production environments for testing, training, and deployment

- Technical integration readiness for current and future interfacing systems

- Operational support readiness, including service management processes, backup procedures, and system monitoring

Where dependencies fall outside the direct scope of the Payment Sytemimplementation such as the supply of hosting infrastructure or external system integrations these will be formally tracked, assessed for impact, and managed through the project’s CRAIDs and governance structures to ensure that they do not compromise implementation timelines or system stability.

The outcome of this readiness process will be a formal Go-Live technical assurance confirming that the technology landscape can sustainably support the THE PAYMENT SYSTEM solution in line with performance, security, and availability expectations. This provides executive confidence, audit traceability, and a controlled transition into the operational environment.

Network capacity planning will:

- Assess current performance

- Forecast future demand

- Identify bottlenecks

- Implement upgrade plans

System deployment will ensure:

- Secure hosting

- Data ownership by the Department

- Cybersecurity controls

- Role-based access

# Deliverables

All deliverables will be developed in accordance with approved standards, baselined through configuration management, and controlled through the change management process to ensure traceability and auditability. Deliverables will include system components, configured modules, data migration outputs, integration interfaces, governance artefacts, training materials, operational procedures, and reporting capabilities required for the successful implementation and institutionalisation of The Payment System.

Acceptance of deliverables will be based on predefined acceptance criteria, sign-off by authorised stakeholders, and alignment with the approved project scope and benefits realisation objectives. This structured approach ensures that outputs are measurable, controlled, and directly contribute to the operational readiness of the Department.

  - Analysis of Programme

This deliverable involves the following:

- Requirements Gathering: Collect detailed requirements from all stakeholders to ensure the system meets their needs.

- System Architecture: Analyse the system architecture, establish hardware requirements, software, and network requirements.

  - Compilation and cleaning of Information

This activity entails the following:

- Collation of programme information: This entails collecting project or programme information that is vital to the proper functioning of the programme.

- Compilation of programme information: group the programme information for ease of data transfer

- Data cleaning: Analysing the information collected and collated to ensure that it is complete, where there are gaps the gaps should be closed. It includes ascertaining that the information is accurate and reported in the correct place.

- Data validation: Entails performing a check on the current data to ensure that it is accurate, consistent, and reflective of its intended purpose.

- Data verification: Entails checking whether data falls within the acceptable range of values:

  - Functional Design Workshops

This deliverable involves the following:

- Design training workshops: This includes the design and development of a workshop for training end-users on the functionality of the system. The intention is to ensure that the end-users will be familiar and continuously learning on the functionality of the system.

- Workshop plan: A rollout plan to workshop the various end-users both at head office, districts and sub-districts to ensure buy-in and use of the system.

- Process Review: Analysis of programme specific procedures to enable workflow creation.

- Workflow Design: Design Programme specific workflows aligned procedures.

  - Data migration to system

This deliverable involves the following:

- Data capturing: Data capture is the process of collecting and storing information from various sources likespreadsheet. . Scanning of participant documentation. is the initial stage in the process and provides several business benefits; however, collecting information from the document is the most valuable value proposition.

- Data migration: The process of selecting, preparing, and moving existing data from one Physical documents to computer database environment to another.

  - Quality Assurance of Data information

This deliverable involves the following:

- Quality Assurance of Data: In today's data-driven landscape, the integrity of data is paramount. Data Quality Assurance serves as the cornerstone of reliable and trustworthy data engineering. Ensuring the accuracy, completeness, and consistency of data has far-reaching implications for informed decision-making, regulatory compliance, and the efficacy of analytical analysis.

- Data Analysis: By manipulating the data using various data analysis techniques and tools, analyse if data complete to provided intended results that are accurate and predictable.

- Interpretation of results: Interpretation of the results to determine if they match the expected output and conduct checks and balances with data on hand.

  - Change Management

To ensure smooth adoption and effective use of the The Paymentsystem across the Department of Public Works and Roads North West by engaging stakeholders, providing clear communication, and delivering targeted training.

Key Components:

Stakeholder Engagement:

- Stakeholder engagement will be facilitated through the Steering Committee and scheduled departmental meetings.

- These meetings will be recurring throughout the project to review progress, address concerns, and gather input.

Communication Plan:

- The communication plan will primarily utilize emails and meetings to disseminate information related to deliverables, project milestones, and reporting.

- This approach will ensure consistent updates and facilitate timely approval of project deliverables.

Training and Capacity Building:

- End users will receive training through in-classroom facilitation sessions aimed at building proficiency in using thePayment System.

- Training sessions will be scheduled in coordination with the department to ensure maximum participation and alignment with operational schedules.

Scheduling:

Training sessions and stakeholder meetings will be scheduled through a joint effort between the Project Portfolio Management Unit (PPMU) and the department to ensure alignment with departmental activities and resource availability.

  - Testing

This deliverable involves the following:

- Installation: Install the necessary hardware and software components.

- Configuration: Configure the system according to the specified requirements.

- System Testing: Conduct thorough testing to ensure the system functions correctly and meets all requirements. System testing, also known as system-level testing, involves evaluating how the various components of an application interact in a fully integrated system. It is carried out on the entire system under either functional or design requirements. It helps you find flaws, gaps, or needs that are lacking from the software application's overall functionality.

- UAT Testing: User engagement will include training and testing in a sandbox environment, where users can explore the system and provide valuable feedback.

- Feedback Loop: Establish a feedback loop to continuously improve the system based on user input

- Documentation: Create comprehensive documentation, including user manuals and technical guides.

  - System Training

This deliverable involves the following:

- Design training workshops: This includes the design and development of a workshop for training end-users on the functionality of the system.

- Training plan: A rollout plan to workshop the various end-users both at head office, districts and sub-districts to ensure buy-in and use of the system.

- System training: Entails developing a training plan with the respective programme once the system has been tested and found to be producing accurate and reliable results once the system has passed the testing.

  - Go-Live and Operational Support

This deliverable involves the following:

- Go-Live: Launch the system and monitor its performance closely.

- Performance Evaluation Reporting: Evaluate the system’s performance against the initial objectives.