DPWWRNW – THE PAYMENT SYSTEM CBP WORKFLOWS

CONTRACT NO: PWR 107/22

DESCRIPTION:	PROJECT, PROGRAMME AND PORTFOLIO MANAGEMENT TO PROJECT, PROGRAMME AND PORTFOLIO MANAGEMENT (PPPM) SERVICES FOR THE NORTH WEST DEPARTMENT OF PUBLIC WORKS AND ROADS FOR A PERIOD OF THIRTY-SIX (36) MONTHS

DOCUMENT CONTROL SHEET

The purpose of this form is to ensure that documents are reviewed and approved prior to issue. The form is to be bound into the front of all documents issued by GO BENG DBG PROJECTS (PTY) LTD JOINT VENTURE

DOCUMENT PROPERTIES

| Item | Description |
| --- | --- |
| Document Title | DPWWRNW – THE PAYMENT SYSTEM CBP WORKFLOWS |
| Client | NORTH WEST PUBLIC WORKS AND ROADS |
| Consultant | GO BENG CONSULTING - DBG PROJECTS (PTY) LTD JOINT VENTURE |
| Document Status | FINAL REPORT |
| Date |  |

VERSION CONTROL

| Version | Prepared By | Signature |
| --- | --- | --- |
| FIRST DRAFT | Stefan van Tonder |  |
| Version | Reviewed By | Signature |
| FIRST REVIEW | Nelisiwe Mnyazana |  |
| Version | Approved By | Signature |
| SECOND REVIEW |  |  |

APPROVED FOR EXTERNAL ISSUE BY

| Version | Approved By | Signature |
| --- | --- | --- |
| FINAL REPORT | Phumza Smith |  |

TABLE OF CONTENTS

1.	WORKFLOW 1: CBP Participant Registration	5

Purpose	5

Trigger	5

Main Roles	5

Special Fields	5

Workflow Stages	6

Workflow Rules	7

2.	WORKFLOW 2: CBP Participant Record Quality Assurance	7

Purpose	7

Ensure participant records are accurate, complete, audit-ready, and compliant for reporting	7

Trigger	7

Main Roles	7

Special Fields	7

Workflow Stages	8

Workflow Rules	8

Notifications	9

3.	WORKFLOW 3: Participant – Time and Attendance	9

Purpose	9

Trigger	9

Main Roles	9

Special Fields	9

Workflow Stages	10

Workflow Rules	11

Notifications	11

4.	WORKFLOW 4: Stipend Payment Approval	11

Purpose	11

Trigger	11

Approved attendance period closed and payroll cycle opened	11

Main Roles	11

Special Fields	12

Workflow Stages	13

Workflow Rules	13

Notifications	13

5.	WORKFLOW 4: CBP Participant Verification	14

Purpose	14

Trigger	14

Main Roles	14

Special Fields	14

Workflow Stages	15

Workflow Rules	15

Notifications	15

6.	Shared Master Status List	15

7.	Recommended Dashboards	16

Participant Operations	16

Attendance Dashboard	16

Payment Dashboard	16

Compliance Dashboard	16

# Phase one Implementation

# WORKFLOW 1: CBP Participant Registration

## Purpose

Capture new participant applications, validate completeness, and route for enrolment approval.

## Trigger

New participant application submitted by official / field officer / data capture.

## Main Roles

- Social Facilitator

- Data Capturer

- Supervisor

- Programme Manager

- QA Officer

## Special Fields

Each of the following steps will require its own special fields which are mandatory to be populated by the main roles.

Step 1 - Personal Details

- First Name

- Last Name

- ID Number

- Date of Birth

- Gender

- Disability Status

- Contact Number

Step 2 - Address Details

- Province

- District

- Ward

- Physical Address

Step 3 -Programme Fields [Next phase]

- Programme Type (EPWP Indirect/ CBP - Direct)

- Intake Batch

- Target Group

- Work Opportunity Type

- Site / Project Allocation

Step 4 - Eligibility Fields [Next phase]

- Age Valid

- SA Citizen

- Unemployed

- Duplicate Check Result

- Eligibility Result

Step 5   Banking Fields

- Bank Name

- Account Holder

- Account Number Masked

- Branch Code

- Bank Verification Status

Step 6 – Supporting Documents

- ID Copy

- Proof of Address

- Consent Form

- Bank Confirmation

- CV (optional)

Step 7 – QA and Approval

- Recommended Outcome

- Approval Outcome

- Rejection Reason

- Return Reason

### Workflow Stages

Draft Capture

↓

Submit Registration

↓

Completeness Check

↓

Eligibility Verification

↓

Banking Verification

↓

Supervisor Review

↓

Approve / Reject

↓

Create Participant Record

↓

Notify Stakeholders

↓

Close

### Workflow Rules

- Mandatory fields required before submit

- Invalid ID number = reject

- Duplicate ID found = route to verification hold

- Missing documents = return for correction

- Approved = auto-create Participant ID

- Rejected = mandatory reason

# WORKFLOW 2: CBP Participant Record Quality Assurance

## Purpose

## Ensure participant records are accurate, complete, audit-ready, and compliant for reporting

## Trigger

Periodic QA cycle / pre-payment review / audit preparation / manager request.

## Main Roles

- Social Facilitator

- QA Officer

- Data Steward

- Supervisor

- Programme Manager

- Internal Audit (read-only)

## Special Fields

Each of the following steps will require its own special fields.

Step 1 -QA Control

- QA Case ID

- Participant ID

- QA Batch

- Review Date

- Reviewer

Step 2 -Data Quality Checks

- Mandatory Fields Complete

- Valid ID Format

- Duplicate Record Check

- Contact Info Complete

- Supporting Docs Present

- Status Accurate

- Site Allocation Valid

- Banking Info Complete

Step 3 - Scoring

- QA Score (%)

- Error Count

- Critical Errors

- Minor Errors

Step 4 – Remediation

- Correction Required

- Assigned Corrector

- Correction Due Date

- Corrective Action Notes

Step 5 – Final Outcome

- Passed QA

- Passed with Corrections

- Failed QA

- Escalated

# Process Flow Participant Record Quality Assurance

### Workflow Stages

QA Batch Created

↓

Assign QA Officer

↓

Record Review

↓

Log Defects

↓

Send for Correction

↓

Recheck Corrected Record

↓

Approve QA Result

↓

Close & Report

### Workflow Rules

- Missing ID = critical fail

- Duplicate participant = critical fail

- Missing banking info = payment hold

- Score below threshold = fail

- Corrections overdue = escalate

- All defects cleared = pass

### Notifications

- QA assigned

- Corrections requested

- Overdue correction

- QA passed

- QA failed

# Phase Two Implementation

# WORKFLOW 3: Participant – Time and Attendance

## Purpose

Capture, validate, approve, and report participant attendance for work performed, training attended, or programme participation days.

## Trigger

Daily attendance capture / weekly submission / monthly attendance close-off

## Main Roles

- Social Facilitator

- Site Supervisor

- Field Officer

- Data Capturer

- Verifier

- Programme Manager

- Payroll Officer

## Special Fields

Each of the following steps will require its own special fields.

Step 1 - Attendance Control

- Attendance Record ID

- Participant ID

- Attendance Period

- Attendance Date

- Site / Project

- Supervisor

Step 2 - Attendance Detail

- Check-In Time

- Check-Out Time

- Hours Worked

- Attendance Status (Present / Absent / Late / Half Day / Leave / Training / Suspended)

- Work Type

Step 3 - Validation Fields

- Duplicate Attendance Check

- Participant Active Status

- Site Allocation Valid

- Approved Days Count

- Overtime Hours (if applicable)

Step 4 - Evidence Fields

- Attendance Captured

- GPS Confirmed

- Biometric Confirmed (optional future)

- Photo Evidence

- Supervisor Comments

Step 5 - Decision Fields

- Submitted By

- Verified By

- Approved By

- Rejection Reason

- Return Reason

Step 6 - Integration Fields

- Payroll Eligible Days

- Export Batch ID

- Locked for Payroll (Yes/No)

### Process Flow Participant – Time and Attendance

### Workflow Stages

Daily Capture

↓

Submit Attendance

↓

Validation Checks

↓

Supervisor Verification

↓

Manager Approval

↓

Lock Attendance Period

↓

Send to Stipend Calculation

↓

Close

### Workflow Rules

- Inactive participant cannot be marked present

- Duplicate same-day attendance blocked

- Missing supervisor evidence = return

- Attendance after cut-off requires override reason

- Approved records locked from editing

- Locked records become available for stipend processing

### Notifications

- Attendance submitted

- Attendance returned

- Attendance approved

- Attendance period locked

- Exceptions flagged

# WORKFLOW 4: Stipend Payment Approval

## Purpose

Calculate stipend due, route for approval, and confirm approved records are eligible for inclusion in the SAGE payment file.

## Trigger

## Approved attendance period closed and payroll cycle opened

## Main Roles

- Social Facilitator

- Site Supervisor

- Field Officer

- Data Capturer

- Verifier

- Programme Manager

- Payroll Officer

## Special Fields

Each of the following steps will require its own special fields.

Step 1 - Payment Control

- Payment Batch ID

- Payroll Period

- Payment Run Date

- Participant ID

- Linked Attendance Batch

Step 2 - Calculation Fields

- Approved Days Worked

- Daily Rate

- Gross Stipend

- Deductions

- Net Pay

- Funding Source

- Cost Centre

Step 3 - Banking Fields

- Bank Name

- Account Holder

- Account Number Masked

- Branch Code

- Bank Verification Status

Step 4 - Validation Fields

- Attendance Approved

- Participant Active

- Banking Complete

- Duplicate Payment Check

- Budget Available

- Exception Flag

Step 5 - Approval Fields

- Prepared By

- Checked By

- Approved By

- Approval Date

- Rejected By

- Rejection Reason

Step 6 - SAGE Export Field

- SAGE Export Status

- Export File Number

- Export Date

- Payment Reference

- Posted to SAGE (Yes/No)

### Process Flow Stipend Payment Approval

### Workflow Stages

Create Payment Batch

↓

Load Eligible Participants

↓

Calculate Stipends

↓

Validation & Exception Check

↓

Finance Review

↓

Manager Approval

↓

Approved for Payment

↓

Generate SAGE Payment File

↓

Mark Exported

↓

Close

### Workflow Rules

- Only approved attendance may be paid

- Missing bank details = exclude from batch

- Duplicate payment in same period blocked

- Negative net pay blocked

- Batch cannot export without approval

- Once exported, records locked

- Rejected records returned for correction

- Approved status = valid for SAGE file inclusion

### Notifications

- Batch created

- Exceptions found

- Batch submitted for approval

- Payment approved

- Payment rejected

- SAGE file generated

- Export completed

# WORKFLOW 4: CBP Participant Verification

## Purpose

Verify that registered participants are legitimate, active, and compliant before placement/payment/reporting.

## Trigger

Approved registration OR scheduled re-verification OR exception flag

## Main Roles

- Social Facilitator

- Verification Officer

- Field Officer

- Supervisor

- Programme Manage

## Special Fields

Each of the following steps will require its own special fields.

Step 1 - Verification Control

- Verification ID

- Linked Participant ID

- Verification Type (Initial / Reverification / Exception)

- Verification Date

- Verification Status

Step 2 - Identity Checks

- ID Confirmed

- Home Affairs Match (optional future)

- Duplicate Match

- Deceased Check (optional future)

Step 3 - Eligibility Checks

- Employment Status Confirmed

- Age Category Confirmed

- Residency Confirmed

- Target Group Confirmed

Step 4 - Attendance / Presence

- Site Visit Completed

- Present on Site

- Supervisor Confirmed

Step 5 - Attendance / Presence

- Photo Captured

- GPS Captured

- Supporting Notes

- Attachments

Step 6 - Attendance / Presence

- Verified Pass

- Verified Fail

- Escalate

- Reason Code

### Process Flow Participant Verification

### Workflow Stages

Verification Triggered

↓

Assign Verification Officer

↓

Desktop Validation

↓

Field Verification (if required)

↓

Supervisor Review

↓

Pass / Fail / Escalate

↓

Update Participant Status

↓

Close

### Workflow Rules

- Failed ID validation = immediate escalation

- No show on site = fail pending investigation

- Missing evidence = return to verifier

- Pass = participant remains active

- Fail = suspend participant

- Escalated = manager review mandatory

### Notifications

- Verification assigned

- Participant flagged

- Verification passed

- Verification failed

- Escalation notice

# Shared Master Status List

Use common statuses across all workflows:

- Draft

- Submitted

- In Review

- Pending Verification

- Pending Approval

- Approved

- Rejected

- Returned for Correction

- Escalated

- Locked

- Exported

- Closed

# Recommended Dashboards

## Participant Operations

- Active participants by Programme Group / District

- New registrations by month / Programme Group / District

- Verification pass/fail rates / Programme Group / District

- QA defect trends

## Attendance Dashboard

- Present vs absent by site / Programme Group / District

- Attendance approval backlog

- Late submissions

- Monthly worked days totals

## Payment Dashboard

- Batches pending approval

- Total stipends approved

- Excluded participants with reasons

- SAGE exports completed

- Payment cycle turnaround time

## Compliance Dashboard

- Duplicate records flagged

- Missing documents

- Overdue workflow items

- Audit exceptions by district